## RAM
RACI Matrix for POS WORLD Corporation
Number of Group: | GROUP 2
Name of Group: | POS WORLD
Name of Project: | POINT OF SALES (POS WORLD)
Project Manager: | SHESHAN ATURUPANA
Enter a Responsibility code (one of: R, A, C, I or '-' ) for each person and activity.
Project Team Members
Name: | Sheshan Aturupana | Sajeewana Deshapriya | Sandamali Marasingha | Buddhika Marasinghe | Chathurika Perera | Sampa Ranasinghe
Role: | Project Manager | Senior Software Engineer | Software Engineer | Quality Assurer | Business Analysist | Client
Starting up a Project
Project Description | A | I | I | I | R | C
Project Brief | A | I | I | I | R | C
Business Case | A | I | I | I | R | C
RACI Matrix | A & R | I | I | I | I | I
Project Mandate | A & R | I | I | I | I | C
Interview Records | A & R | I | I | I | I | C
Initiating a Project
System Requirement Specification | A | I | I | I | R | C
Project Initation Document | A & R | I | I | I | I | C
Project Plan | A | C | C | C | R | I
Project Quality Plan | A | C | C | C | R | I
Communication Plan | A | C | C | C | R | I
Highlight Records | A & R | I | I | I | I | I
Risk Management Plan | A | C | C | C | R | I
Lessons Learned Report | A | C | C | C | R | I
Test Plan | A | C | C | R | R | I
Managing a Project
Risk Log | A & R | I | I | I | I | I
Quality Log | A & R | I | I | I | I | I
Lessons Learned Log | A & R | I | I | I | I | I
Issue Log | A & R | I | I | I | I | I
Request for Change | A & R | I | I | I | I | I
Daily Log | A & R | I | I | I | I | I
Work Breakdown Structure | A & R | I | I | I | I | I
Gantt Chart | A & R | C | C | C | C | I
Entity Relationship Diagram | A & R | C | C | I | I | I
Use Case Diagram | A & R | C | C | I | I | I
Controlling & Managing Stage
GUI Design - Initial | A | C | C | C | R | I
GUI Developing - Initial | A | R | R | C | C | I
GUI Testing - Initial | A | C | C | R | C | I
GUI Aprovel - Initial | A & R | C | C | C | C | I
Prototype 1 - Demostrating | A | C | C | R | R | I
Prototype 1 - Version 1 - Release | A | R | R | R | I | C
Feedback Gethoring from Release 1 | A | I | I | C | R | R
GUI Design - Final | A | C | C | C | R | I
GUI Developing - Final | A | R | R | C | C | I
GUI Testing - Final | A | C | C | R | C | I
GUI Aprovel - Final | A & R | C | C | C | C | I
Prototype 2 - Demostrating | A | C | C | R | R | I
Prototype 2 - Version 2 - Release | A | R | R | R | I | C
Feedback Gethoring from Release 2 | A | I | I | C | R | R
Test Report - Unit | A | R | R | C | C | I
Test Report - GUI | A | C | C | R | C | I
Test Report - Functional | A | C | C | R | C | I
Test Report - Integration | A | C | C | R | C | I
Test Report - Proformance | A | C | C | R | C | I
Test Report - Regration | A | C | C | R | C | I
Test Report - Smoke | A | C | C | R | C | I
Defect - Report | A | R | C | R | C | I
Finalised Project | A | R | R | R | C | I
Closing Project | A | C | C | I | R | I
Training Plan | A | C | C | C | R | C
Evaluation Gathering | A | I | I | I | R | I
Evaluation Report | A | C | C | C | R | I
User Manual | A | C | C | C | R | I
Video | A | C | C | C | R | I
PPT Presentation | A | I | I | I | R | C
Production Release Note | A | C | C | R | R | I
Production Release | A | R | C | R | C | I
Production Release - Feedback | A | I | I | I | C | R
Client Meeting Minutes | A | I | I | I | R | -
Definitions
A | Accountable | Responsible for success/failure of this activity
R | Responsible | Does the work to achieve the task
C | Consulted | Provides input for the task
I | Informed | Must be informed about progress and output of the task.

## Definitions
Definitions
Code
A | Accountable | Responsible for success/failure of this activity
R | Responsible | Does the work to achieve the task
C | Consulted | Provides input for the task
I | Informed | Must be informed about progress and output of the task.